## Project Plan
Jumpy Street
Project Lead
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
UI and menus |  | Allison | Done
Start and end screens |  | Allison | Done
Pause screens |  | Allison | In Progress
Grid for movement |  | Alec | In Progress
Nodes system for movement and spawning |  | Alec | Not Implemented
Player movement across nodes |  | Alec | Done
Continuous spawn and despawn |  | Nelson | In Progress
Moving grid upand down instead of moving player |  | Alec | In Progress
Buffered inputs so that the player can tap a certain time before the hop ends and still go, or change movement |  | Alec | Not Implemented
Terrain Spawner |  | Nelson | In Progress
Pre made chunks of terrain |  | Nelson | Not Implemented
A way to spawn terrain on nodes |  | Nelson | In Progress
A way to check spawned terrain to ensure it is traversable |  | Nelson | Not Implemented
Pre generated terrain that wil spawn randomly |  | Nelson | Not Implemented
Scrapping levels that are not traversable |  | Nelson | Not Implemented
Continious Obstacle Spawner |  | Alec | In Progress
A system to spawn moving obstacles |  | Alec | In Progress
System to move them in horizontal lanes |  | Alec | In Progress
Movement not being tied to nodes so it is more smooth |  | Alec | In Progress
Inherited Movement on Obstacles |  | Nelson | In Progress
Moving obstacles |  | Nelson | In Progress
A way for the movement to pass onto player to change net motion |  | Nelson | In Progress
A random spawner that leaves intervals in which player can move between |  | Nelson | Not Implemented
Death States for types of terrain and obstacles |  | Allison | In Progress
A way to check if player is on object or hit by it |  | Allison | In Progress
A way to check type of terrain is on a node to see if it is safe to walk on |  | Alec | Done
A way to check if a moving obstacle can be walked on |  | Alec | Done
This includes space outside game which will kill |  | Alec | Done
Insert a row above to add more features to the list.